## Submittal Impact Database
Area | File No. | File Name | Revision | Date | Current Contents | Impact Status | Impact Description | Action Proposed (Millenia to do)
3-25 | 1 | 1. By Tourmaline/03-25-080-15_SCHA Letter_Environmental Effects Assessment.pdf | Not stated | 2025-01-31 | Schedule A / SCHA environmental effects assessment correspondence. | Change Candidate | The report states "The Site is planned to be entirely within the existing development already constructed and permitted. See Appendix A for the survey plan and associated maps. As the Site is already constructed, with no new disturbance or soil stripping requirements, a Schedule A is not required." Does the proposed expansion of the settling pond constitute a ground "disturbance, or soil stripping"? | None.
3-25 | 2 | 1. By Tourmaline/100120203_C5+ and Inlet Compressor_PE Report_BRFN.pdf | Not stated | 2024-12-01 | PE notification/report package for C5+ and inlet compressor scope. | No Change Expected | No concerns noted with project and changes don't appear to be of the nature that would change this. | None.
3-25 | 3 | 1. By Tourmaline/100120203_C5+ and Inlet Compressor_PE Report_DRFN.pdf | Not stated | 2024-12-01 | PE notification/report package for C5+ and inlet compressor scope. | No Change Expected | No concerns noted with project and changes don't appear to be of the nature that would change this. | None.
3-25 | 4 | 1. By Tourmaline/100120203_C5+ and Inlet Compressor_PE Report_HRFN.pdf | Not stated | 2025-01-01 | PE notification/report package for C5+ and inlet compressor scope. | No Change Expected | No concerns noted with project and changes don't appear to be of the nature that would change this. | None.
3-25 | 5 | 1. By Tourmaline/100120203_C5+ and Inlet Compressor_PE Report_MLIB.pdf | Not stated | 2025-01-01 | PE notification/report package for C5+ and inlet compressor scope. | No Change Expected | No concerns noted with project and changes don't appear to be of the nature that would change this. | None.
3-25 | 6 | 1. By Tourmaline/100120203_C5+ and Inlet Compressor_PE Report_SFN.pdf | Not stated | 2025-01-01 | PE notification/report package for C5+ and inlet compressor scope. | No Change Expected | No concerns noted with project and changes don't appear to be of the nature that would change this. | None.
3-25 | 7 | 1. By Tourmaline/100120203_C5+ and Inlet Compressor_PE Report_WMFN.pdf | Not stated | 2025-01-01 | PE notification/report package for C5+ and inlet compressor scope. | No Change Expected | No concerns noted with project and changes don't appear to be of the nature that would change this. | None.
3-25 | 8 | 1. By Tourmaline/2024 Tourmaline Fugitive Emission Management Plan (Signed).pdf | 2024 | 2023-10-02 | Corporate fugitive emission management plan. | Not in Review Scope | Corporate policy, not in Millenia scope | None.
3-25 | 9 | 1. By Tourmaline/3-25 West Doe Project Schedule.pdf | Not stated | 2025-02-03 | One-page project schedule/objective summary. | Change Required | Update to new scope and timeframe | None.
3-25 | 10 | 1. By Tourmaline/BCER Project Description Form - 3-25 West Doe (2025-01-31).pdf | Not stated | 2025-01-31 | BCER project description form for 3-25. | Change Required | Re-issue project description with current equipment list, process narrative, shared utilities, incinerator/flare boundary, LACT OUT, and 4-25 stabilization/SOC interface. | Propose changes / make comments.
3-25 | 11 | 1. By Tourmaline/Tourmaline Plant Supervision Summary.pdf | Not stated | 2017-07-05 | General plant supervision summary. | Not in Review Scope | This is a purely operational decision and NOT something that Millenia needs to weigh in on. | None.
3-25 | 12 | 1. By Tourmaline/Tourmaline Sand Management Plan - Revisions July 26, 2017.pdf | Revisions July 26, 2017 | 2021-10-12 | General sand management plan. | Not in Review Scope | This is just a statement on letterhead, not a formal policy. But also not something Millenia needs to weigh in on. | None.
3-25 | 13 | 1. By Tourmaline/West Doe Gathering (2025-02-03).pdf | 2025-01-01 | 2025-02-03 | West Doe gathering-system context document. | Not in Review Scope | This is outside of the context of the facility, not something Millenia needs to weigh in on. | None.
3-25 | 14 | BFD-242510-100_200_300 (3-25 Doe)_Block Flow Diagram_rA.pdf | rA | 2024-11-22 | Block flow diagram. | Change Required | Revise blocks and interfaces for retired 3-25 dehydration/stabilizer/SOC/heat-medium, non-regenerative treating, VRU to 4-25 SOC, shared IA/fuel gas/power, and incinerator/flare boundary. | Create new revision
3-25 | 15 | CIV-242510-5001 & 5002 (3-25 Doe)_Plot Plan_rC.pdf | rC | 2024-11-22 | Civil plot plan set. | Change Required | Remove or relabel retired units/plot reservations, update incinerator/shared flare location/interface, LACT boundary, heat-medium/instrument-air assumptions, and affected package layout. | Create new revision
3-25 | 16 | MFS-242510 (3-25 Doe)_P&ID_rA.pdf | rA | 2024-12-10 | P&ID package. | Change Required | Revise process, utility, relief, control, shutdown, and interface sheets for all retired/relocated units and new shared utility/VRU/incinerator bases. | Create new revision
3-25 | 17 | MSS-242510-1001 (3-25 Doe)_Metering Schematic_rA.pdf | rA | 2024-12-06 | Metering schematic. | Change Candidate | Confirm on-site 3-25 LACT units. | Not in Millenia scope as far as the project execution, but may provide assistance if this is still TOU scope.
3-25 | 18 | PFD-242510 (3-25 Doe)_Process Flow Diagram_rA.pdf | rA | 2024-11-22 | Process flow diagram package. | Change Required | Update process flow paths, material interfaces, utility ties, and removed equipment blocks; add/clarify 4-25 SOC and 4-25 IA interfaces. | Create new revision
3-25 | 19 | W242510-CIV-REP-000001-001 (3-25 Doe)_Surface Water Management Plan_rA.pdf | rA | 2023-09-27 | Surface water management plan. | Change Required | Revise according to new stormwater retainment pond design. | Create new revision
3-25 | 20 | W242510-ELC-REP-000001-001 (3-25 Doe)_Light Assessment_rA.pdf | rA | 2024-11-05 | Light assessment. | Change Required | Update project description and lighting inventory according to new Plot Plan | Create new revision
3-25 | 21 | W242510-ELC-REP-000002-001 (3-25 Doe)_Ground Permissive at Truck-Out_rA.pdf | rA | 2024-11-12 | Ground permissive at truck-out philosophy. | Not in Review Scope | Corporate policy, not in Millenia scope | None.
3-25 | 22 | W242510-PRC-DBM-000001-001 (3-25 Doe)_DBM_rA.pdf | rA | 2024-12-17 | Design basis memorandum. | Change Required | Rewrite DBM sections for removed/retired scope, process selection, shared utilities, 4-25 interfaces, flare/incinerator basis, horsepower, package roster, and supersession notes. | Create new revision
3-25 | 23 | W242510-PRC-HMB-000001-001 (3-25 Doe)_HMB_rA.pdf | rA | 2024-11-22 | Heat and material balance. | Change Required | Recalculate HMB around removed stabilization/SOC/heat-medium/dehydration, non-regenerative treating, VRU discharge, and shared IA demands where represented. | Create new revision
3-25 | 24 | W242510-PRC-REG-000001-001 (3-25 Doe)_Emissions Summary_rA.pdf | rA | 2024-12-02 | Emissions summary. | Change Required | Recalculate emissions for removed heat-medium/stabilizer/SOC/dehydration sources, changed incinerator/feed basis, VRU routing, and shared utilities. | Create new revision
3-25 | 25 | W242510-PRC-REP-000001-001 (3-25 Doe)_Non-Flare Connected PSV Summary_rA.pdf | rA | 2023-09-13 | Non-flare connected PSV summary. | Change Required | Remove retired equipment PSV entries, update relief/non-flare classification, and confirm current inlet separator/caustic/flare boundary PSV basis. | Create new revision
3-25 | 26 | W242510-PRC-REP-000002-001 (3-25 Doe)_Inlet Separator Summary_rA.pdf | rA | 2024-11-04 | Inlet separator summary. | Change Required | Update to twin 9 ft x 40 ft horizontal 3-phase basis, plot for third as applicable, downstream 4-25 stabilization/SOC context, and current interface conditions. | Create new revision
3-25 | 27 | W242510-PRC-REP-000003-001 (3-25 Doe)_Prime Mover List_rA.pdf | rA | 2024-11-06 | Prime mover list. | Change Required | Remove or reclassify retired prime movers, update inlet-compressor drive/VFD basis, standby generator strategy, and local IA/heat-medium equipment. | Create new revision
3-25 | 28 | W242510-PRC-REP-000004-001 (3-25 Doe)_Facility Shutdown & Blowdown Philosophy_rA.pdf | rA | 2024-11-26 | Shutdown and blowdown philosophy. | Change Required | Update shutdown/blowdown scenarios, cause/effect assumptions, relief/blowdown destination, retired units, shared IA/power, and 4-25 SOC interface. Remove "Emergency Generator" reference. | Create new revision
3-25 | 29 | W242510-PRC-REP-000005-001 (3-25 Doe)_Flare Stack Data Submission_rA.pdf | rA | 2024-11-26 | Flare stack data submission. | Change Required | Recalculate flare/incinerator loads and update shared flare/incinerator boundary, retired relief sources, and non-regenerative caustic/incinerator feed basis. | Create new revision
3-25 | 30 | W242510-PRC-REP-000007-001 (3-25 Doe)_DEOS_rB.pdf | rB | 2024-11-12 | DEOS report. | Change Required | No longer dehydrating at this site. Possibly remove from application | Update list of references, possibly explain why it's been removed.
3-25 | 31 | W242510-PRC-REP-000008-001 (3-25 Doe)_Safety and Loss Management_rA.pdf | rA | 2023-09-27 | Safety and loss management report. | Change Required | Update safety narrative due to retired/relocated units, shared utilities, flare/incinerator, or shutdown/blowdown changes alter safeguards or responsibilities. | Create new revision
3-25 | 32 | W242510-PRJ-LST-000003-001 (3-25 Doe)_HAZMAT List_rA.pdf | rA | 2024-11-18 | Hazardous materials list. | Change Required | Remove/adjust chemicals tied to retired condensate dehydration, heat-medium and local IA systems; spent caustic/DSO basis under non-regenerative treating. | Create new revision
3-25 | 33 | W242510-PRJ-QAP-000001-001 (3-25 Doe)_QAP & Validation Report_rA.pdf | rA | 2023-10-13 | QAP and validation report. | Change Required | Project description is outdated. The contents are generic management system stuff. Unclear if Tourmaline wants to just re-use much of the generic content` | Create new revision
3-25 | 34 | W242510-PRJ-REP-000001-001 (3-25 Doe)_Secondary Containment Plan_rA.pdf | rA | 2023-09-27 | Secondary containment plan. | Change Required | Update containment volumes/areas and material list for removed units, LACT boundary, non-regenerative caustic, spent caustic/DSO, and retained tanks. | Create new revision
3-25 | 35 | W242510-PRJ-REP-000002-001 (3-25 Doe)_Adopted Codes & Standards_rA.pdf | rA | 2024-11-04 | Adopted codes and standards. | Change Required | Remove NFPA 30, as a minimum | Revised list of adopted codes and standards.
3-25 | 36 | W242510-PRJ-REP-000003-001 (3-25 Doe)_Facility Security and Fire Protection_rA.pdf | rA | 2024-11-04 | Facility security and fire protection. | Change Required | Project description is outdated. The contents are generic management system stuff. Unclear if Tourmaline wants to just re-use much of the generic content` | Create new revision
3-25 | 37 | W242510-PRJ-REP-000004-001(3-25 Doe)_HAZID Study Report_rA.pdf | rA | 2024-12-11 | HAZID study report. | Change Required | Reconcile HAZID nodes/scenarios and referenced documents with retired units, new interfaces, non-regenerative treating, shared flare/incinerator, and changed utilities. | Create new revision
3-25 | 38 | W242510-PRJ-REP-000005-001 (3-25 Doe)_Prelim Consequence Assessment_rA.pdf | rA | 2023-10-13 | Preliminary consequence assessment. | Change Required | Re-run scenario basis for removed/relocated equipment, changed relief/incinerator loads, changed hazardous inventory, and current shutdown/blowdown assumptions. | Create new revision
3-25 | 39 | W242510-PRJ-REP-000006-001 (3-25 Doe)_Noise Impact Assessment_r2.pdf | r2 | 2025-01-14 | Noise impact assessment. | Change Required | Rebuild noise model inventory to remove retired local units, update 4-25 shifted sources/interfaces, IA consolidation, incinerator location, and current equipment counts. | Create new revision
4-25 | 1 | 1. By Tourmaline/02-25-080-15W6_Revision Letter_Pre-Con Env Assessment_26Sep2023.pdf | Revision letter | 2023-09-26 | Pre-construction environmental assessment revision letter. | No Change Expected | Nothing in the scope changes appears to have any bearing on the assessment that was performed. It's all still the same types of activities. | None.
4-25 | 2 | 1. By Tourmaline/2-25 Project Description Form Final Draft_V2-20231102.pdf | V2 | 2023-11-02 | Project description form. | Change Required | Update project description for NGL rather than LPG, depropanizer removal, current stabilizer/SOC scope, shared incinerator, and instrument air serving both facilities. | Create new revision
4-25 | 3 | 1. By Tourmaline/2024 Tourmaline Fugitive Emission Management Plan (Al Signed).pdf | Signed | 2023-10-02 | Corporate fugitive emission management plan. | Not in Review Scope | Corporate policy, not in Millenia scope | None.
4-25 | 4 | 1. By Tourmaline/8-33 to West Doe Map.pdf | Not stated | 2023-09-28 | Route/context map. | Not in Review Scope | This is outside of the context of the facility, not something Millenia needs to weigh in on. | None.
4-25 | 5 | 1. By Tourmaline/Tourmaline Plant Supervision Plan.pdf | Not stated | 2017-07-05 | Plant supervision plan. | Not in Review Scope | This is a purely operational decision and NOT something that Millenia needs to weigh in on. | None.
4-25 | 6 | 1. By Tourmaline/Tourmaline Sand Management Plan - Revisions July 26, 2017.pdf | Revisions July 26, 2017 | 2021-10-12 | Sand management plan. | Not in Review Scope | This is just a statement on letterhead, not a formal policy. But also not something Millenia needs to weigh in on. | None.
4-25 | 7 | 1. By Tourmaline/West Doe Gas Plant Proliferation Review.pdf | Not stated | 2017-06-23 | Gas plant proliferation review. | Not in Review Scope | This is a purely commercial decision and NOT something that Millenia needs to weigh in on. | None.
4-25 | 8 | 1. By Tourmaline/West Doe Gathering System Schematic.pdf | Not stated | 2023-10-05 | Gathering system schematic. | Not in Review Scope | This is outside of the context of the facility, not something Millenia needs to weigh in on. | None.
4-25 | 9 | 1. By Tourmaline/West Doe Project Schedule.pdf | Not stated | 2023-10-17 | Project schedule. | Change Required | Update to new timeframe. | Create new revision
4-25 | 10 | 006810-NIA-000 (4-25 Doe)_Noise Impact Assessment_r0.pdf | r0 | 2023-11-30 | Noise impact assessment. | Change Required | Rebuild acoustic inventory and scenarios for LPG-to-NGL, depropanizer removal, stabilizer/SOC consolidation, IA consolidation, heat medium changes, and shared incinerator. | Create new revision
4-25 | 11 | 100118719_FAC_2 25-80-15W6 (4-25 Doe)_PE Report.pdf | Not stated | 2023-10-31 | Facility PE report. | No Change Expected | No concerns noted with project and changes don't appear to be of the nature that would change this. | File role; targeted SCA evidence changes the engineered facility basis.
4-25 | 12 | BFD-235633-100_200_5100 (4-25 Doe)_Block Flow Diagram_rC.pdf | rC | 2023-10-26 | Block flow diagram. | Change Required | Revise process blocks for NGL current scope, depropanizer removal, non-regenerative treating, IA consolidation, heat medium, mole sieve, stabilizer/SOC, and shared incinerator. | Create new revision
4-25 | 13 | CIV-235633-5001 (4-25 Doe)_Plot Plan_rK.pdf | rK | 2024-10-24 | Civil plot plan sheet. | Change Required | Update layout for removed depropanizer/LPG future scope, current NGL packages, stabilizer/SOC consolidation, IA building, heat-medium configuration, and incinerator interface. | Create new revision
4-25 | 14 | CIV-235633-5002 (4-25 Doe)_Plot Plan_rK.pdf | rK | 2025-04-21 | Civil plot plan package. | Change Required | Plot plan has substantially changed. | Create new revision
4-25 | 15 | MFS-235633 (4-25 Doe)_P&ID_rA.pdf | rA | 2023-10-27 | P&ID package. | Change Required | Revise process, utility, relief, controls, and interface sheets for all current NGL, stabilizer/SOC, heat medium, IA, incinerator, and electrical decisions. | Create new revision
4-25 | 16 | MSS-235633-1001 (4-25 Doe)_Metering Schematic_rB.pdf | rB | 2025-04-21 | Metering schematic. | Change Required | Project depiction is obsolete. Revise flow diagram and change labels to reflect NGL rather than LPG/C3-C4/depropanizer framing and no retired product stream remains. | Create new revision
4-25 | 17 | PFD-235633 (4-25 Doe)_Process Flow Diagram_rB.pdf | rB | 2023-10-26 | Process flow diagram package. | Change Required | Update all flow paths and balances for NGL, removed depropanizer, stabilizer/SOC consolidation, inlet HEX, heat medium, TEG/mole sieve, IA, and incinerator basis. | Create new revision
4-25 | 18 | W235633-CIV-REP-000001-001 (4-25 Doe)_Surface Water Management Plan_rB.pdf | rB | 2023-09-27 | Surface water management plan. | Change Required | Project description is obsolete. Check drainage/containment assumptions for current NGL/stabilizer/IA/heat-medium package layout and removed LPG/depropanizer scope. | Create new revision
4-25 | 19 | W235633-ELC-REP-000001-001 (4-25 Doe)_Light Assessment_rC.pdf | rC | 2023-09-26 | Light assessment. | Change Required | Update lighting inventory and project description if package layout or current equipment differs from the submitted assessment. | Create new revision
4-25 | 20 | W235633-ELC-REP-000002-001 (4-25 Doe)_Ground Permissive at Truck-Out_rB.pdf | rB | 2023-09-26 | Ground permissive at truck-out philosophy. | Not in Review Scope | Corporate policy, not in Millenia scope | None.
4-25 | 21 | W235633-PRC-DBM-000001-001 (4-25 Doe)_Design Basis Memorandum_rA.pdf | rA | 2023-10-23 | Design basis memorandum. | Change Required | Rewrite DBM sections for current NGL, depropanizer removal, non-regenerative treating, stabilizer/SOC scope, heat medium, TEG/mole sieve, IA, incinerator, electrical, and package roster. | Create new revision
4-25 | 22 | W235633-PRC-HMB-000001-001 (4-25 Doe)_HMB Winter_rC.pdf | rC | 2023-10-24 | Winter HMB. | Change Required | Recalculate winter HMB for NGL, no depropanizer, non-regenerative treating, changed heat medium, TEG/mole sieve, IA demand, and incinerator feed. | Create new revision
4-25 | 23 | W235633-PRC-HMB-000002-001 (4-25 Doe)_HMB Summer_rC.pdf | rC | 2023-10-24 | Summer HMB. | Change Required | Same as winter HMB, with summer operating basis and heat/refrigeration balance reviewed separately. | Create new revision
4-25 | 24 | W235633-PRC-REG-000001-001 (4-25 Doe)_Emissions Summary_rB.pdf | rB | 2024-10-23 | Emissions summary. | Change Required | Recalculate emissions for removed depropanizer/LPG equipment, NGL treating, heat medium, IA, incinerator, stabilizer/SOC, flare, and equipment roster. | Create new revision
4-25 | 25 | W235633-PRC-REP-000001-001 (4-25 Doe)_Non-Flare Connected PSV Summary_rA.pdf | rA | 2023-09-29 | Non-flare connected PSV summary. | Change Required | Remove retired depropanizer/LPG PSV basis and update current NGL, stabilizer/SOC, heat medium, IA, and relief/non-flare classification. | Create new revision
4-25 | 26 | W235633-PRC-REP-000002-001 (4-25 Doe)_Inlet Separator Summary.pdf | Not stated | 2023-09-29 | Inlet separator summary. | Change Required | Update to current two 9 ft x 40 ft installed separators, future third plot, and inlet-separator HEX / MPFF preheat relationship. | Create new revision
4-25 | 27 | W235633-PRC-REP-000003-001 (4-25 Doe)_Prime Mover List_rC.pdf | rC | 2023-03-01 | Prime mover list. | Change Required | Update drivers/motors for current stabilizer/SOC, heat medium, TEG/mole sieve, instrument air, VFD, capacitor-bank removal, and standby power basis; remove depropanizer/LPG equipment if present. | Create new revision
4-25 | 28 | W235633-PRC-REP-000004-001 (4-25 Doe)_Plant Shutdown & Blowdown Philosophy_rB.pdf | rB | 2023-09-29 | Shutdown and blowdown philosophy. | Change Required | Update shutdown/blowdown causes, relief destinations, current NGL process, depropanizer removal, heat medium, IA, and incinerator/shared interface responsibilities. | Create new revision
4-25 | 29 | W235633-PRC-REP-000005-001 (4-25 Doe)_Flare Stack Data Submission_rA.pdf | rA | 2023-10-27 | Flare stack data submission. | Change Required | Recalculate flare/incinerator loads and feed basis; remove caustic-regeneration/depropanizer relief bases; identify 3-25 physical incinerator location. | Create new revision
4-25 | 30 | W235633-PRC-REP-000007-001 (4-25 Doe)_DEOS_rB.pdf | rB | 2023-10-25 | DEOS report. | Change Required | Project description is obsolete LPG/depropanizer/non-current incinerator assumptions. | Create new revision
4-25 | 31 | W235633-PRC-REP-000008-001 (4-25 Doe)_Safety & Loss Management_rA.pdf | rA | 2023-09-27 | Safety and loss management report. | Change Required | Update safety narrative if NGL/depropanizer removal, shared incinerator, IA, heat medium, or shutdown/blowdown changes alter safeguards or responsibilities. | Create new revision
4-25 | 32 | W235633-PRJ-LST-000003-001 (4-25 Doe)_HAZMAT List_rC.pdf | rC | 2023-09-27 | Hazardous materials list. | Change Required | Replace LPG/depropanizer-related chemicals with current NGL/DSO/spent caustic basis; update heat medium, IA dryer, TEG/mole sieve consumables. | Create new revision
4-25 | 33 | W235633-PRJ-QAP-000001-001 (4-25 Doe)_QAP & Validation Report_rA.pdf | rA | 2023-10-19 | QAP and validation report. | Change Required | Project description is outdated. The contents are generic management system stuff. Unclear if Tourmaline wants to just re-use much of the generic content` | Create new revision
4-25 | 34 | W235633-PRJ-REP-000001-001 (4-25 Doe)_Secondary Containment Plan_rB.pdf | rB | 2023-09-27 | Secondary containment plan. | Change Required | Update containment basis for NGL instead of LPG, no depropanizer, non-regenerative caustic, DSO/spent caustic, heat medium, and package layout changes. | PDF text hits depropanizer/LPG/NGL/heat medium/incinerator/spent caustic.
4-25 | 35 | W235633-PRJ-REP-000002-001 (4-25 Doe)_Adopted Codes & Standards_rB.pdf | rB | 2023-09-27 | Adopted codes and standards. | Change Required | Remove NFPA 30, as a minimum | Revised list of adopted codes and standards.
4-25 | 36 | W235633-PRJ-REP-000003-001 (4-25 Doe)_Facility Security & Fire Protection_rC.pdf | rC | 2023-09-27 | Facility security and fire protection. | Change Candidate | Confirm fire/security coverage reflects current equipment layout, hazardous inventory, and shared incinerator/utility responsibility. | PDF text includes LPG/NGL/heat medium/flare/mole sieve terms.
4-25 | 37 | W235633-PRJ-REP-000004-001 (4-25 Doe)_HAZID Study Report_r0.pdf | r0 | 2023-10-05 | HAZID study report. | Change Required | Reconcile HAZID nodes/scenarios and referenced documents with depropanizer removal, NGL basis, non-regenerative caustic, IA, heat medium, mole sieve, and shared incinerator. | Create new revision
4-25 | 38 | W235633-PRJ-REP-000005-001 (4-25 Doe)_Prelim Consequence Assessment_rA.pdf | rA | 2023-10-13 | Preliminary consequence assessment. | Change Required | Re-run consequence basis for removed/changed equipment, changed inventory, shared incinerator, relief/blowdown, and utility interfaces. | Create new revision
4-25 | 39 | W235633-PRJ-REP-000006-001 (4-25 Doe)_Design Change Summary_rB.pdf | rB | 2023-09-27 | Design change summary. | Change Required | Rewrite change summary to capture depropanizer out, NGL current scope, stabilizer/SOC consolidation, instrument air serving both facilities, heat medium, HEX, mole sieve, incinerator, and standby/VFD/capacitor electrical changes. | Create new revision