# 12 Rules for Project Management

- A Project is comprised of Packages

- Packages are comprised of Deliverables

- Deliverables are comprised of Documents

- Documents are completed through Tasks

- Tasks are managed through the 9 Domains

- Tasks are tracked at the level of Deliverables

- Decisions are tracked at the level of Packages

- Documents are ‘statused’ daily as part of the weekly sprint log

- Deliverables are ‘statused’ weekly with planning for now, next, and later

- Packages are ‘statused’ weekly with planning for the 6 week lookahead (to be integrated into the master schedule)

- A coordinator role takes ownership of the task tracker but task responsibility is allocated to specific people and resources

- Communication occurs in all channels and the responsible member(s) must update the tracker at least weekly with essential information

    - Document status changes

    - If a “HOLD” status, what: decision, information, resources, approval

    - Any decisions that were made (changes to scope are transferred to the decision log)

    - Discussions and meetings