## RAIL
|  |  | ARTIFACTS RAIL | [6 empty] | DROPDOWN LISTS:
|  |  | DATE / VERSION: | [7 empty] | PACKAGE | ARTIFACT TYPE | STATUS | HOLD TYPES | PRIORITY | NEXT APPROVAL STEP
|  |  | PROJECT NAME: | [9 empty] | In Progress | Decision | Now | IFA
|  |  | PROJECT NO.: | [9 empty] | On Hold | Information | Next | IFR
|  |  | DOC NO.: | [9 empty] | Complete | Clarification | Later | IFH
[13 empty] | Cancelled | Resources | After | Squad Check
| Item # | PACKAGE | ARTIFACT TYPE | ARTIFACT ID# | STATUS | HOLD TYPES | PRIORITY | NEXT APPROVAL STEP | NEXT TARGET DATE |  |  |  | Risk of Change | Approval |  | IRT
1 | ART-1 | [14 empty] | IFC
2 | ART-2 | [14 empty] | Issue Interally
3 | ART-3 | [14 empty] | Issue for Use
4 | ART-4
5 | ART-5
6 | ART-6
7 | ART-7
8 | ART-8
9 | ART-9
10 | ART-10
11 | ART-11
12 | ART-12
13 | ART-13
14 | ART-14
15 | ART-15
16 | ART-16
17 | ART-17
18 | ART-18
19 | ART-19
20 | ART-20
21 | ART-21
22 | ART-22
23 | ART-23
24 | ART-24
25 | ART-25
26 | ART-26
27 | ART-27
28 | ART-28
29 | ART-29
30 | ART-30
31 | ART-31
32 | ART-32
33 | ART-33
34 | ART-34
35 | ART-35
36 | ART-36
37 | ART-37
38 | ART-38
39 | ART-39
40 | ART-40
41 | ART-41
42 | ART-42
43 | ART-43
44 | ART-44
45 | ART-45
46 | ART-46
47 | ART-47
48 | ART-48
49 | ART-49
50 | ART-50
51 | ART-51
52 | ART-52
53 | ART-53
54 | ART-54
55 | ART-55
56 | ART-56
57 | ART-57
58 | ART-58
59 | ART-59
60 | ART-60
61 | ART-61
62 | ART-62
63 | ART-63
64 | ART-64
65 | ART-65
66 | ART-66
67 | ART-67
68 | ART-68
69 | ART-69
70 | ART-70
71 | ART-71
72 | ART-72
73 | ART-73
74 | ART-74
75 | ART-75
76 | ART-76
77 | ART-77
78 | ART-78
79 | ART-79
80 | ART-80
81 | ART-81
82 | ART-82
83 | ART-83
84 | ART-84
85 | ART-85
86 | ART-86
87 | ART-87
88 | ART-88
89 | ART-89
90 | ART-90
91 | ART-91
92 | ART-92
93 | ART-93
94 | ART-94
95 | ART-95
96 | ART-96
97 | ART-97
98 | ART-98
99 | ART-99
100 | ART-100
101 | ART-101
102 | ART-102
103 | ART-103
104 | ART-104
105 | ART-105
106 | ART-106
107 | ART-107
108 | ART-108
109 | ART-109
110 | ART-110
111 | ART-111
112 | ART-112
113 | ART-113
114 | ART-114
115 | ART-115
116 | ART-116
117 | ART-117
118 | ART-118
119 | ART-119
120 | ART-120
121 | ART-121
122 | ART-122
123 | ART-123
124 | ART-124
125 | ART-125
126 | ART-126
127 | ART-127
128 | ART-128
129 | ART-129
130 | ART-130
131 | ART-131
132 | ART-132
133 | ART-133
134 | ART-134
135 | ART-135
136 | ART-136
137 | ART-137
138 | ART-138
139 | ART-139
140 | ART-140
141 | ART-141
142 | ART-142
143 | ART-143
144 | ART-144
145 | ART-145
146 | ART-146
147 | ART-147
148 | ART-148
149 | ART-149
150 | ART-150
151 | ART-151
152 | ART-152
153 | ART-153
154 | ART-154
155 | ART-155
156 | ART-156
157 | ART-157
158 | ART-158
159 | ART-159
160 | ART-160
161 | ART-161
162 | ART-162
163 | ART-163
164 | ART-164
165 | ART-165
166 | ART-166
167 | ART-167
168 | ART-168
169 | ART-169
170 | ART-170
171 | ART-171
172 | ART-172
173 | ART-173
174 | ART-174
175 | ART-175
176 | ART-176
177 | ART-177
178 | ART-178
179 | ART-179
180 | ART-180
181 | ART-181
182 | ART-182
183 | ART-183
184 | ART-184
185 | ART-185
186 | ART-186
187 | ART-187
188 | ART-188
189 | ART-189
190 | ART-190
191 | ART-191
192 | ART-192
193 | ART-193
194 | ART-194
195 | ART-195
196 | ART-196
197 | ART-197
198 | ART-198
199 | ART-199
200 | ART-200
201 | ART-201
202 | ART-202
203 | ART-203
204 | ART-204
205 | ART-205
206 | ART-206
207 | ART-207
208 | ART-208
209 | ART-209
210 | ART-210
211 | ART-211
212 | ART-212
213 | ART-213
214 | ART-214
215 | ART-215
216 | ART-216
217 | ART-217
218 | ART-218
219 | ART-219
220 | ART-220
221 | ART-221
222 | ART-222
223 | ART-223
224 | ART-224
225 | ART-225
226 | ART-226
227 | ART-227
228 | ART-228
229 | ART-229
230 | ART-230
231 | ART-231
232 | ART-232
233 | ART-233
234 | ART-234
235 | ART-235
236 | ART-236
237 | ART-237
238 | ART-238
239 | ART-239
240 | ART-240
241 | ART-241
242 | ART-242
243 | ART-243
244 | ART-244
245 | ART-245
246 | ART-246
247 | ART-247
248 | ART-248
249 | ART-249
250 | ART-250
251 | ART-251
252 | ART-252
253 | ART-253
254 | ART-254
255 | ART-255
256 | ART-256
257 | ART-257
258 | ART-258
259 | ART-259
260 | ART-260
261 | ART-261
262 | ART-262
263 | ART-263
264 | ART-264
265 | ART-265
266 | ART-266
267 | ART-267
268 | ART-268
269 | ART-269
270 | ART-270
271 | ART-271
272 | ART-272
273 | ART-273
274 | ART-274
275 | ART-275
276 | ART-276
277 | ART-277
278 | ART-278
279 | ART-279
280 | ART-280
281 | ART-281
282 | ART-282
283 | ART-283
284 | ART-284
285 | ART-285
286 | ART-286
287 | ART-287
288 | ART-288
289 | ART-289
290 | ART-290
291 | ART-291
292 | ART-292
293 | ART-293
294 | ART-294
295 | ART-295
296 | ART-296
297 | ART-297
298 | ART-298
299 | ART-299
300 | ART-300
301 | ART-301
302 | ART-302
303 | ART-303
304 | ART-304
305 | ART-305
306 | ART-306
307 | ART-307
308 | ART-308
309 | ART-309
310 | ART-310
311 | ART-311
312 | ART-312
313 | ART-313
314 | ART-314
315 | ART-315
316 | ART-316
317 | ART-317
318 | ART-318
319 | ART-319
320 | ART-320
321 | ART-321
322 | ART-322
323 | ART-323
324 | ART-324
325 | ART-325
326 | ART-326
327 | ART-327
328 | ART-328
329 | ART-329
330 | ART-330
331 | ART-331
332 | ART-332
333 | ART-333
334 | ART-334
335 | ART-335
336 | ART-336
337 | ART-337
338 | ART-338
339 | ART-339
340 | ART-340
341 | ART-341
342 | ART-342
343 | ART-343
344 | ART-344
345 | ART-345
346 | ART-346
347 | ART-347
348 | ART-348
349 | ART-349
350 | ART-350
351 | ART-351
352 | ART-352
353 | ART-353
354 | ART-354
355 | ART-355
356 | ART-356
357 | ART-357
358 | ART-358
359 | ART-359
360 | ART-360
361 | ART-361
362 | ART-362
363 | ART-363
364 | ART-364
365 | ART-365
366 | ART-366
367 | ART-367
368 | ART-368
369 | ART-369
370 | ART-370
371 | ART-371
372 | ART-372
373 | ART-373
374 | ART-374
375 | ART-375
376 | ART-376
377 | ART-377
378 | ART-378
379 | ART-379
380 | ART-380
381 | ART-381
382 | ART-382
383 | ART-383
384 | ART-384
385 | ART-385
386 | ART-386
387 | ART-387
388 | ART-388
389 | ART-389
390 | ART-390
391 | ART-391
392 | ART-392
393 | ART-393
394 | ART-394
395 | ART-395
396 | ART-396
397 | ART-397
398 | ART-398
399 | ART-399
400 | ART-400
401 | ART-401
402 | ART-402
403 | ART-403
404 | ART-404
405 | ART-405
406 | ART-406
407 | ART-407
408 | ART-408
409 | ART-409
410 | ART-410
411 | ART-411
412 | ART-412
413 | ART-413
414 | ART-414
415 | ART-415
416 | ART-416
417 | ART-417
418 | ART-418
419 | ART-419
420 | ART-420
421 | ART-421
422 | ART-422
423 | ART-423
424 | ART-424
425 | ART-425
426 | ART-426
427 | ART-427
428 | ART-428
429 | ART-429
430 | ART-430
431 | ART-431
432 | ART-432
433 | ART-433
434 | ART-434
435 | ART-435
436 | ART-436
437 | ART-437
438 | ART-438
439 | ART-439
440 | ART-440
441 | ART-441
442 | ART-442
443 | ART-443
444 | ART-444
445 | ART-445
446 | ART-446
447 | ART-447
448 | ART-448
449 | ART-449
450 | ART-450
451 | ART-451
452 | ART-452
453 | ART-453
454 | ART-454
455 | ART-455
456 | ART-456
457 | ART-457
458 | ART-458
459 | ART-459
460 | ART-460
461 | ART-461
462 | ART-462
463 | ART-463
464 | ART-464
465 | ART-465
466 | ART-466
467 | ART-467
468 | ART-468
469 | ART-469
470 | ART-470
471 | ART-471
472 | ART-472
473 | ART-473
474 | ART-474
475 | ART-475
476 | ART-476
477 | ART-477
478 | ART-478
479 | ART-479
480 | ART-480
481 | ART-481
482 | ART-482
483 | ART-483
484 | ART-484
485 | ART-485
486 | ART-486
487 | ART-487
488 | ART-488
489 | ART-489
490 | ART-490
491 | ART-491
492 | ART-492
493 | ART-493
494 | ART-494
495 | ART-495
496 | ART-496
497 | ART-497
498 | ART-498
499 | ART-499
500 | ART-500
501 | ART-501
502 | ART-502
503 | ART-503
504 | ART-504
505 | ART-505
506 | ART-506
507 | ART-507
508 | ART-508
509 | ART-509
510 | ART-510
511 | ART-511
512 | ART-512
513 | ART-513
514 | ART-514
515 | ART-515
516 | ART-516
517 | ART-517
518 | ART-518
519 | ART-519
520 | ART-520
521 | ART-521
522 | ART-522
523 | ART-523
524 | ART-524
525 | ART-525
526 | ART-526
527 | ART-527
528 | ART-528
529 | ART-529
530 | ART-530
531 | ART-531
532 | ART-532
533 | ART-533
534 | ART-534
535 | ART-535
536 | ART-536
537 | ART-537
538 | ART-538
539 | ART-539
540 | ART-540
541 | ART-541
542 | ART-542
543 | ART-543
544 | ART-544
545 | ART-545
546 | ART-546
547 | ART-547
548 | ART-548
549 | ART-549
550 | ART-550
551 | ART-551
552 | ART-552
553 | ART-553
554 | ART-554
555 | ART-555
556 | ART-556
557 | ART-557
558 | ART-558
559 | ART-559
560 | ART-560
561 | ART-561
562 | ART-562
563 | ART-563
564 | ART-564
565 | ART-565
566 | ART-566
567 | ART-567
568 | ART-568
569 | ART-569
570 | ART-570
571 | ART-571
572 | ART-572
573 | ART-573
574 | ART-574
575 | ART-575
576 | ART-576
577 | ART-577
578 | ART-578
579 | ART-579
580 | ART-580
581 | ART-581
582 | ART-582
583 | ART-583
584 | ART-584
585 | ART-585
586 | ART-586
587 | ART-587
588 | ART-588
589 | ART-589
590 | ART-590
591 | ART-591
592 | ART-592
593 | ART-593
594 | ART-594
595 | ART-595
596 | ART-596
597 | ART-597
598 | ART-598
599 | ART-599
600 | ART-600
601 | ART-601
602 | ART-602
603 | ART-603
604 | ART-604
605 | ART-605
606 | ART-606
607 | ART-607
608 | ART-608
609 | ART-609
610 | ART-610
611 | ART-611
612 | ART-612
613 | ART-613
614 | ART-614
615 | ART-615
616 | ART-616
617 | ART-617
618 | ART-618
619 | ART-619
620 | ART-620
621 | ART-621
622 | ART-622
623 | ART-623
624 | ART-624
625 | ART-625
626 | ART-626
627 | ART-627
628 | ART-628
629 | ART-629
630 | ART-630
631 | ART-631
632 | ART-632
633 | ART-633
634 | ART-634
635 | ART-635
636 | ART-636
637 | ART-637
638 | ART-638
639 | ART-639
640 | ART-640
641 | ART-641
642 | ART-642
643 | ART-643
644 | ART-644
645 | ART-645
Note on O2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The Critical Distinction Project-level HOLDs: Cross organizational boundaries (between disciplines, to/from client, to/from third parties) Require project leadership intervention Affect project baselines (scope/schedule/budget) Stop work or risk major rework if not resolved Must be logged and tracked Discipline-level HOLDs: Internal to a discipline or individual Handled through normal professional judgment or horizontal coordination Aren't holding up other disciplines or project baselines Part of routine work execution Should NOT be logged as project-level Action Items
Note on P2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NOW = blocking other work or deadline is imminent so drop other plans if necessary to focus on this NEXT = will become a NOW within the next 2 - 3 weeks so planning is still possible LATER = not NOW, nor NEXT but is idenfitied within 6-week lookahead so planning is expected AFTER = beyond 6-week lookahead, so no planning is expected
Note on N3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What this tells you: Someone is working on obtaining the decision/information/clarification/resource/approval No obstacles are preventing progress Expected to move toward completion on the tracked timeline What this is NOT: Sitting idle waiting for someone to start Blocked by something else Completed but not yet verified
Note on O3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What it is: A choice between alternatives that affects scope, schedule, budget, or crosses organizational boundariesExamples: "Should we use approach A or B for the structural system?" (affects multiple disciplines downstream) "Does the client want Option 1 or Option 2?" (changes what gets delivered) "Do we meet the aggressive schedule or add resources?" (project baseline decision) Who decides: Project leadership, client, or someone with authority across boundariesWhy it's a project-level HOLD: The decision affects multiple people/disciplines, changes project baselines, or requires external input. Work cannot proceed until decided because proceeding on assumptions risks major rework.Framework mechanism: Logged as Action Item, tracked in Decision Log, associated with affected deliverables
Note on P3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Attention must be given to this because it's blocking other work OR deadline is imminent. drop other plans if necessary
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Meaning: The coordination action is blocked and cannot progress until something else resolves. What this tells you: Progress has stopped There's a specific blocking condition Requires intervention to unblock What this is NOT: Just slow progress (that's still "In Progress") Low priority (that might be "In Progress" but deprioritized) Waiting for normal review cycles (that's still "In Progress") Key distinction from In Progress: Something specific is preventing any progress. The action cannot advance until the blocker is removed.
Note on O4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What it is: Required input from outside the discipline/organization that work depends on Examples: "We need the client's design standards document to proceed with any calculations" "We need the civil drawings showing column locations before we can design foundations" "We need the regulatory approval letter before we can proceed to next phase" "We need survey data from the third-party surveyor" Who provides it: Client, other disciplines, third parties, regulators Why it's a project-level HOLD: The information crosses organizational boundaries. Without it, the work either cannot start or will be based on assumptions that might require complete rework. Framework mechanism: Logged as Action Item, assigned to whoever must obtain it, tracked until received
Note on P4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is expected to become a NOW within 2-3 weeks. But there's still enough time for this to be planned for according to the guidance of the 6-week lookahead in the combined project schedule, and the targeted completion dates in this action log
Note on N5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Meaning: The coordination action has been resolved and no longer requires tracking. What this tells you: The decision was made The information was received The clarification was obtained The resource was secured The approval was granted The outcome is documented What this is NOT: "We think we have what we need" (not verified) "Mostly done but waiting on one small thing" (not complete) "We decided to proceed without it" (that's Cancelled) Key requirement: There must be a clear outcome that can be documented. What was the decision? What information was received? What clarification was provided?
Note on O5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What it is: Ambiguity in scope, requirements, or intent that must be resolved by someone outside the discipline Examples: "The contract says 'adequate ventilation' but doesn't specify rates - what does client actually require?" "Drawing shows 10 units but specification says 12 - which is correct?" "Client email says 'ASAP' but what's the actual deadline?" "Scope says 'design to code' but which edition of the code applies?" Who clarifies: Client, project leadership, contract administrator, or authority that set the requirement Why it's a project-level HOLD: The ambiguity affects what gets delivered, potentially scope/cost/schedule. Proceeding on interpretation risks delivering wrong thing. Needs external clarification to resolve. Framework mechanism: Logged as Action Item, assigned to whoever must obtain clarification, decision logged once received
Note on P5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is identified as a requirement within the 6-week planning horizon so some effort on planning is expected
Note on N6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Meaning: The coordination action is no longer needed and will not be completed. What this tells you: Circumstances changed The underlying need went away The question is now moot Pursuing it would be wasted effort What this is NOT: Failed to complete (use "On Hold" with explanation) Deferred to later phase (should stay "In Progress" or "On Hold") Key distinction from Complete: Nothing was resolved. The need simply went away.
Note on O6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What it is: Lack of people, tools, budget, or access required to execute the work Examples: "We need a structural PE to sign off on these calcs but none are available" "We need specialized software license but don't have budget approval" "The assigned engineer is overloaded on 3 other projects and has no capacity" "We need site access to do the survey but client hasn't provided clearance" "We need to hire a subconsultant for specialty work but need approval" Who provides: Project leadership, management, client, or external parties Why it's a project-level HOLD: The resource constraint crosses boundaries or requires management intervention. The work cannot proceed without escalation. Framework mechanism: Logged as Action Item, escalated to whoever can authorize/provide the resource
Note on P6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This falls outside the 6-week planning horizon so nothing is expected. It can be opportunity work and has been logged as an action item so it can be tracked.
Note on D7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From Master Deliverables List and also internal deliverables (PWPs but shared internally between disciplines)
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actions respond only to these needs: information, clarification, resources, decisions, approvals
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: See comments in dropdown list
Note on G7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: See comments in dropdown list
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Comes from Deliverables RAIL and 6-week lookahead
Note on I7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Disciplines are required to plan with the approvals process in mind. The approvals process is project specific. See dropdown lists for more information.
Note on J7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: YYYY-MM-DD Based on project schedule / 6-week lookahead and following the PRIORITY in column G
Note on N7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Meaning: The coordination action is progressing, but circumstances suggest the requirement itself might change, potentially invalidating the work. What this tells you: Currently "In Progress" on the stated requirement But there's active discussion/indication that the requirement might shift Proceeding, but with awareness that the target might move Need to monitor for potential pivot Examples: "Proceeding with design for 12 units per contract, but client has mentioned budget pressures and possible reduction to 10" (work continues but might need to change) "Obtaining approval for Schedule A, but client is considering extending timeline which would affect what we're asking approval for" (the ask might change) "Developing options for client decision, but stakeholder dynamics suggest new requirements might emerge before decision" (decision criteria might shift) What this is NOT: Blocked (that's "On Hold") Vague uncertainty about everything (that's just normal project risk) Someone's random speculation (there needs to be concrete indication of potential change) Key distinction from In Progress: You're flagging that effort might be wasted if circumstances change. This creates awareness so leadership can decide whether to: Continue and accept potential rework risk Pause until situation clarifies Seek clarification to lock down the requirement Why this status exists: Prevents the situation where someone spends 2 weeks on something, then leadership says "oh yeah, we knew that might change, we should have told them to wait."
Note on O7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What it is: Formal sign-off required before work can proceed or be issued Examples: "Design is complete and ready for PE seal before issuing to client" "Deliverable ready for project manager review before submitting for milestone" "Approach complete and needs client approval before proceeding with detailed design" "Change affects budget and needs sponsor approval before implementing" Who approves: Someone with formal authority - PE, PM, client, sponsor, regulator Why it's a project-level HOLD: The approval is a formal gate. Work downstream cannot start, or deliverable cannot be issued, until approval obtained. Affects project progress across boundaries. Framework mechanism: Logged as Action Item, deliverable marked as "ready for approval," tracked through approval process