## Master Deliverables List
Synthetic Deliverables Register (TWD-shaped fixture)
Document No | Title | Package | Discipline | Owner | Current Rev | State | Due Date | Remarks
MDL-0001 | Synthetic pump datasheet | PKG-01 | Mechanical | pe@example.test | A | in_work | 2026-07-09 | 42
MDL-0002 | Synthetic valve list | PKG-02 | Mechanical | pe@example.test | B | issued | 2026-08-01 | TRUE
MDL-0003 | [6 empty] | 2026-01-15

## Rules of Credit
ENGINEERING & DESIGN
Issued for Review | 30
Issued for Construction

## Lists
Working Status
Not Started
In Progress
Complete