## Packages
ID # | WBS | CoA Tracking Number | Packages | Discipline | Process Piping | Utility Piping | Relief / Flare / Vent | Drain / Containment | Electrical Power | EHT | Grounding / Bonding | Area / Exterior Lighting | Cathodic Protection | I&C / Control Cabling | Communications / Network | Building HVAC / Services | Fire & Gas / Safety Systems | Maintenance Access | Grading / Site Drainage / Spill Containment | Structural / Foundations / Supports | Product Loading | Pipeline / Pigging | Interface Review Notes
1 | 01 | 26020-01-42-001 | Earthworks for foundations | Civil | [14 empty] | X | X
2 | 02 | 26020-01-42-001 | Earthworks for foundations | Civil | [14 empty] | X | X
3 | 01 | 26020-01-42-003 | Site Grading | Civil |  |  |  | X | [10 empty] | X
4 | 02 | 26020-01-42-003 | Site Grading | Civil |  |  |  | X | [10 empty] | X
5 | 03 | 26020-01-42-003 | Site Grading | Civil |  |  |  | X | [10 empty] | X
6 | 03 | 26020-03-42-006 | Containment Berms | Civil |  |  |  | X | [10 empty] | X
7 | 02 | 26020-02-42-007 | Retention Pond | Civil |  |  |  | X | [10 empty] | X
8 | 01 | 26020-01-32-001 | Controls system design and integration | Controls | X | X | X |  | X |  |  |  |  | X | X | X | X | [5 empty] | Confirm whether controls power-panel interfaces should be tracked separately.
9 | 02 | 26020-01-32-001 | Controls system design and integration | Controls | X | X | X |  | X |  |  |  |  | X | X | X | X | [5 empty] | Confirm whether controls power-panel interfaces should be tracked separately.
10 | 03 | 26020-01-32-001 | Controls system design and integration | Controls | X | X | X |  | X |  |  |  |  | X | X | X | X | [5 empty] | Confirm whether controls power-panel interfaces should be tracked separately.
106 |  | 26020-01-30-001 | Yard Lighting | Electrical |  |  |  |  | X |  | X | X
11 | 02 | 26020-02-30-002 | 4160V SWITCHGEAR EQUIPMENT | Electrical |  |  |  |  | X |  | X |  |  | X | X |  |  | X |  | X
12 | 02 | 26020-02-30-003 | 10KVA AC UNINTERRUPTIBLE POWER SUPPLY | Electrical |  |  |  |  | X |  | X | [6 empty] | X |  | X
13 | 02 | 26020-02-30-004 | 100A DC UNINTERUPTIBLE POWER SUPPLY | Electrical |  |  |  |  | X |  | X | [6 empty] | X |  | X
14 | 02 | 26020-02-30-005 | CONTACTOR PANELS - LIGHTING / EXHAUST FAN CONTACTOR PANELS - LOW VOLTAGE | Electrical |  |  |  |  | X |  | X | X |  | X | X |  |  | X |  | X
15 | 02 | 26020-02-30-006 | Transformer TXP-8300-1 - STEP DOWN DISTRIBUTION TRANSFORMER - 12/15MVA 13.8kV/4160/2400V | Electrical |  |  |  |  | X |  | X | X |  | X | X |  |  | X |  | X
16 | 02 | 26020-02-30-007 | Transformer TXP-8200-1 - STEP DOWN DISTRIBUTION TRANSFORMER - 3MVA 13.8kV/600/347V | Electrical |  |  |  |  | X |  | X | X |  | X | X |  |  | X |  | X
17 | 02 | 26020-02-30-008 | MV VFD - 600HP, 4160V, 3PH, 60HZ - 4160V VFD | Electrical |  |  |  |  | X |  | X |  |  | X | X |  |  | X |  | X
18 | 02 | 26020-02-30-009 | MV VFD - 5000HP, 4160V, 3PH, 60HZ - 4160V VFD | Electrical |  |  |  |  | X |  | X |  |  | X | X |  |  | X |  | X
19 | 02 | 26020-02-30-009 | MV VFD - 5000HP, 4160V, 3PH, 60HZ - 4160V VFD | Electrical |  |  |  |  | X |  | X |  |  | X | X |  |  | X |  | X
20 | 01 | 26020-01-30-011 | 13.8kV SWITCHGEAR EQUIPMENT | Electrical |  |  |  |  | X |  | X |  |  | X | X |  |  | X |  | X
21 | 01 | 26020-01-30-012 | 6.9kV SWITCHGEAR EQUIPMENT | Electrical |  |  |  |  | X |  | X |  |  | X | X |  |  | X |  | X
22 | 01 | 26020-01-30-013 | 5kV SWITCHGEAR EQUIPMENT | Electrical |  |  |  |  | X |  | X |  |  | X | X |  |  | X |  | X
23 | 01 | 26020-01-30-014 | MV VFD - 1500HP, 4160V, 3PH, 60HZ - 4160V VFD | Electrical |  |  |  |  | X |  | X |  |  | X | X |  |  | X |  | X
24 | 01 | 26020-01-30-015 | MV VFD - 2000HP, 4160V, 3PH, 60HZ - 4160V VFD | Electrical |  |  |  |  | X |  | X |  |  | X | X |  |  | X |  | X
25 | 01 | 26020-01-30-016 | MV VFD - 5000HP, 6.9kV, 3PH, 60HZ - 6.9kV VFD | Electrical |  |  |  |  | X |  | X |  |  | X | X |  |  | X |  | X
26 | 02 | 26020-02-30-017 | Transformer TXP-8300-2 - STEP DOWN DISTRIBUTION TRANSFORMER - 20/26MVA 13.8kV/6.9kV/0.4kV | Electrical |  |  |  |  | X |  | X | X |  | X | X |  |  | X |  | X
27 | 01 | 26020-01-30-018 | Transformer TXP-8301-1 - STEP DOWN DISTRIBUTION TRANSFORMER - 20/26MVA 13.8kV/6.9kV/0.4kV | Electrical |  |  |  |  | X |  | X | X |  | X | X |  |  | X |  | X
28 | 01 | 26020-01-30-019 | Transformer TXP-8801-1 - STEP DOWN DISTRIBUTION TRANSFORMER - 7.5MVA 13.8kV/4160/2400V | Electrical |  |  |  |  | X |  | X | X |  | X | X |  |  | X |  | X
29 | 01 | 26020-01-30-020 | Transformer TXP-8600-1 - STEP DOWN DISTRIBUTION TRANSFORMER - 2.5MVA 13.8kV/600/347V | Electrical |  |  |  |  | X |  | X | X |  | X | X |  |  | X |  | X
30 | 01 | 26020-01-30-021 | Transformer TXP-8200-1 - STEP DOWN DISTRIBUTION TRANSFORMER - 2.5MVA 13.8kV/600/347V | Electrical |  |  |  |  | X |  | X | X |  | X | X |  |  | X |  | X
31 | 01 | 26020-01-30-022 | Transformer TXP-8500-1 - STEP DOWN DISTRIBUTION TRANSFORMER - 3MVA 13.8kV/600/347V | Electrical |  |  |  |  | X |  | X | X |  | X | X |  |  | X |  | X
32 | 03 | 26020-03-30-023 | Cathodic Protection Design and Installation | Electrical |  |  |  |  | X |  | X |  |  | X | X
33 | 02 | 26020-02-30-024 | 4160V SWITCHGEAR ELECTRICAL BUILDING (830-2) | Electrical |  | X |  | X | X |  | X | X |  | X | X | X | X | X | X | X
34 | 02 | 26020-02-30-025 | 600V ELECTRICAL BUILDING (820-2) | Electrical |  | X |  | X | X |  | X | X |  | X | X | X | X | X | X | X
35 | 01 | 26020-01-30-026 | 13.8kV SWITCHGEAR ELECTRICAL BUILDING (810-1) | Electrical |  | X |  | X | X |  | X | X |  | X | X | X | X | X | X | X
36 | 01 | 26020-01-30-027 | 6.9kV SWITCHGEAR ELECTRICAL BUILDING (830-1) | Electrical |  | X |  | X | X |  | X | X |  | X | X | X | X | X | X | X
37 | 01 | 26020-01-30-028 | 5kV SWITCHGEAR ELECTRICAL BUILDING (880-1) | Electrical |  | X |  | X | X |  | X | X |  | X | X | X | X | X | X | X
38 | 01 | 26020-01-30-029 | 600V ELECTRICAL BUILDING (820-1) | Electrical |  | X |  | X | X |  | X | X |  | X | X | X | X | X | X | X
39 | 01 | 26020-01-30-030 | 600V ELECTRICAL BUILDING (850-1) | Electrical |  | X |  | X | X |  | X | X |  | X | X | X | X | X | X | X
40 | 01 | 26020-01-30-031 | 600V ELECTRICAL BUILDING (860-1) | Electrical |  | X |  | X | X |  | X | X |  | X | X | X | X | X | X | X
41 | 01 | 26020-01-30-032 | 13.8kV, 3.0MW STANDBY GENERATOR BUILDING (490-1) | Electrical |  | X |  | X | X |  | X | X |  | X | X | X | X | X | X | X
42 | 03 | 26020-03-39-010 | Control Room Building | Electrical |  | X |  | X | X |  | X | X |  | X | X | X | X |  | X | X
43 | 01 | 26020-01-32-002 | Instrumentation (outside of Mechanical Packages only) | Instrumentation | X | X |  |  | X |  |  |  |  | X | X | [7 empty] | Field supports, power, and comms not marked unless confirmed by package scope.
44 | 02 | 26020-01-32-002 | Instrumentation (outside of Mechanical Packages only) | Instrumentation | X | X |  |  | X |  |  |  |  | X | X | [7 empty] | Field supports, power, and comms not marked unless confirmed by package scope.
45 | 03 | 26020-01-32-002 | Instrumentation (outside of Mechanical Packages only) | Instrumentation | X | X |  |  | X |  |  |  |  | X | X | [7 empty] | Field supports, power, and comms not marked unless confirmed by package scope.
46 | 01 | 26020-01-12-001 | Acid Gas Compressors | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
73 | 01 | 26020-01-27-001 | Amine Treating Unit | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
88 | 02 | 26020-02-27-001 | Caustic Treating (Condensate Mercaptan Removal) | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
74 | 01 | 26020-01-27-002 | Caustic Treating (NGL Mercaptan Removal) | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
75 | 01 | 26020-01-27-003 | Cryogenic Unit ("Deepcut") | Mechanical | X | X | X | X | X |  | X | X |  | X |  | X | X | X |  | X
53 | 01 | 26020-01-17-001 | Flare KO Drum (Cryo) | Mechanical | X |  | X | X | X | X | X |  |  | X |  |  |  | X |  | X
81 | 02 | 26020-02-17-001 | Flare KO Drum (High Pressure) 3-25 | Mechanical | X |  | X | X | X | X | X | X |  | X |  |  |  | X |  | X
54 | 01 | 26020-01-17-002 | Flare KO Drum (High Pressure) 4-25 | Mechanical | X |  | X | X | X | X | X | X |  | X |  |  |  | X |  | X
82 | 02 | 26020-02-17-002 | Flare KO Drum (Low Pressure) 3-25 | Mechanical | X |  | X | X | X | X | X | X |  | X |  |  |  | X |  | X
55 | 01 | 26020-01-17-003 | Flare KO Drum (Low Pressure) 4-25 | Mechanical | X |  | X | X | X | X | X | X |  | X |  |  |  | X |  | X
85 | 02 | 26020-02-25-001 | Flare Stack (High Pressure) | Mechanical |  | X | X | X | X |  | X |  |  | X |  |  | X |  |  | X
86 | 02 | 26020-02-25-002 | Flare Stack (Low Pressure) | Mechanical |  | X | X | X | X |  | X |  |  | X |  |  | X |  |  | X
84 | 02 | 26020-02-23-001 | Fuel Gas Skid 3-25 | Mechanical | X | X | X | X | X |  | X | X |  | X |  | X | X | X |  | X
71 | 01 | 26020-01-23-001 | Fuel Gas Skid 4-25 | Mechanical | X | X | X | X | X |  | X | X |  | X |  | X | X | X |  | X
52 | 01 | 26020-01-16-001 | Inlet / TEG Dehy Cross Exchanger | Mechanical | X | X |  | X |  | X | X | X |  | X |  |  |  | X |  | X
100 | 03 | 26020-03-27-001 | Hydrogen Peroxide Sweetening Unit | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
87 | 02 | 26020-02-25-003 | Incinerator | Mechanical | X | X | X | X | X |  | X | X |  | X |  | X | X | X |  | X
48 | 01 | 26020-01-12-003 | Inlet / Sales Compressors | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
80 | 02 | 26020-02-12-001 | Inlet Compressors | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
83 | 02 | 26020-02-17-003 | Inlet Separators 3-25 | Mechanical | X | X | X | X |  | X | X | X |  | X |  |  | X | X |  | X
56 | 01 | 26020-01-17-004 | Inlet Separators 4-25 | Mechanical | X | X | X | X |  | X | X | X |  | X |  |  | X | X |  | X
79 | 01 | 26020-01-39-001 | Instrument Air Building | Mechanical |  | X |  | X | X |  | X | X |  | X |  | X | X | X |  | X
76 | 01 | 26020-01-29-001 | Lube Oil Supply | Mechanical |  | X |  | X | X |  | X | X |  | X |  |  |  | X |  | X
58 | 01 | 26020-01-17-006 | Medium Pressure Flash Feed Separator | Mechanical | X |  |  | X |  | X | X | X |  | X |  |  | X | X |  | X
77 | 01 | 26020-01-29-002 | Methanol Injection | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
69 | 01 | 26020-01-22-002 | Mole Sieve Drier Unit (Gas) | Mechanical | X |  | X | X | X | X | X | X |  | X |  | X | X | X |  | X
70 | 01 | 26020-01-22-003 | Mole Sieve Drier Unit (NGL) | Mechanical | X |  | X | X | X | X | X | X |  | X |  | X | X | X |  | X
61 | 01 | 26020-01-18-002 | NGL Booster and Transfer Pumps Building | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
62 | 01 | 26020-01-18-003 | NGL Loading Pumps Building | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
89 | 02 | 26020-02-35-001 | Pig Receivers (Inlet) 3-25 | Mechanical | X |  | X | X | X | X |  |  |  | X |  |  |  | X | X | X |  | X
78 | 01 | 26020-01-35-001 | Pig Receivers (Inlet) 4-25 | Mechanical | X |  | X | X | X | X |  |  |  | X |  |  |  | X | X | X |  | X
51 | 01 | 26020-01-15-001 | Process Heat Medium Unit | Mechanical |  | X |  | X | X |  | X | X |  | X |  | X | X | X |  | X
49 | 01 | 26020-01-12-004 | Sales Gas Booster Compressor | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
50 | 01 | 26020-01-12-005 | Stabilizer Overheads Compressors | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
57 | 01 | 26020-01-17-005 | Stabilizers | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
59 | 01 | 26020-01-17-007 | Storage Bullets | Mechanical | X |  | X | X |  | X | X | X |  | X |  |  |  | X | X | X
91 | 03 | 26020-03-18-001 | Tank Farm Pump Building 3-25 | Mechanical | X | X | X | X | X | X | X | X | X | X |  | X | X | X | X | X
60 | 01 | 26020-01-18-001 | Tank Farm Pump Building 4-25 | Mechanical | X | X | X | X | X | X | X | X | X | X |  | X | X | X |  | X
94 | 03 | 26020-03-19-002 | Tanks, Caustic (API 650) 3-25 | Mechanical | X |  | X | X |  |  | X | X | X | X |  |  |  |  | X | X
65 | 01 | 26020-01-19-003 | Tanks, Caustic (API 650) 4-25 | Mechanical | X |  | X | X |  |  | X | X | X | X |  |  |  |  | X | X
97 | 03 | 26020-03-19-006 | Tanks, Condendate (API 650) 3-25 | Mechanical | X |  | X | X |  |  | X | X | X | X |  |  |  |  | X | X
66 | 01 | 26020-01-19-004 | Tanks, Condendate (API 650) 4-25 | Mechanical | X |  | X | X |  |  | X | X | X | X |  |  |  |  | X | X
63 | 01 | 26020-01-19-001 | Tanks, DSO (API 650) | Mechanical | X |  | X | X |  |  | X | X | X | X |  |  |  |  | X | X
95 | 03 | 26020-03-19-004 | Tanks, Slop (API 650) | Mechanical | X |  | X | X |  |  | X | X | X | X |  |  |  |  | X | X
96 | 03 | 26020-03-19-005 | Tanks, Sour Condendate (API 650) | Mechanical | X |  | X | X |  |  | X | X | X | X |  |  |  |  | X | X
98 | 03 | 26020-03-19-007 | Tanks, Sour Water (API 650) 3-25 | Mechanical | X |  | X | X |  |  | X | X | X | X |  |  |  |  | X | X
67 | 01 | 26020-01-19-005 | Tanks, Sour Water (API 650) 4-25 | Mechanical | X |  | X | X |  |  | X | X | X | X |  |  |  |  | X | X
93 | 03 | 26020-03-19-001 | Tanks, Water (API 650) 3-25 | Mechanical | X |  | X | X |  |  | X | X | X | X |  |  |  |  | X | X
64 | 01 | 26020-01-19-002 | Tanks, Water (API 650) 4-25 | Mechanical | X |  | X | X |  |  | X | X | X | X |  |  |  |  | X | X
68 | 01 | 26020-01-22-001 | TEG Dehydration Unit | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
99 | 03 | 26020-03-23-001 | Truck Product Loading Unit 3-25 | Mechanical | X |  |  | X | X |  | X | X |  | X |  | X | X |  | X | X | X
72 | 01 | 26020-01-23-001 | Truck Product Loading Unit 4-25 | Mechanical | X |  |  | X | X |  | X | X |  | X |  | X | X |  | X | X | X
90 | 03 | 26020-03-12-001 | Vapour Recovery Unit 3-25 | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
47 | 01 | 26020-01-12-002 | Vapour Recovery Unit 4-25 | Mechanical | X | X | X | X | X | X | X | X |  | X |  | X | X | X |  | X
101 | 01 | 26020-01-36-001 | Precast concrete foundations | Structural | [14 empty] | X | X
102 | 01 | 26020-01-36-002 | Monolithic concrete foundations | Structural | [14 empty] | X | X
103 | 03 | 26020-03-36-003 | Pipe Rack Modules | Structural | X | X | X |  | X | X |  |  |  | X | X |  |  |  | X | X |  |  | Rack-supported commodities should be confirmed against plot plan/model.
104 | 01 | 26020-01-36-004 | Structural steel - outside of modules | Structural | [14 empty] | X | X
105 | 01 | 26020-01-36-005 | Platforms | Structural | [7 empty] | X | [6 empty] | X | X |  |  | Platform-to-equipment tie-ins should be confirmed by layout/model.